## Cover
Scrum Reporting Form
| Day | 2023-04-20
| Due Date | 2023-04-21
| Team Name: | Apesh
| Team Members: | Aiden and Deepesh
| Project: | Sudoku
Division of Labor
| Module Name | Author
You have had an opportunity to decide on a project and start the general set-up for the project. The next step is to go through and identify all the tasks that need to be commpleted to have a finished product for the Final Project Presentation. The Fibonacci Sequence to assign importance of each task. Rate the tasks by the importance of when they need to be done as well as the importance to the completion of the project. Some tasks with a low priority may never be completed. Those can be saved for a later project. Come back to this list each day, mark tasks that have been completed as "Done" and repriotize the remaining tasks.
| Plans for | 2023-04-21
| Team Member | Tasks planned | Prriority
| All | Decide on Project | 1
| All | Identify major parts of the project | 2
| All | Set up GitHub account and invite all participants | 3
| Story behind your project | Have you ever been bored and wanted something to do to challenge your brain? Well here is the solution for you! Play sudoku today, a free to play game with hours of painful entertainment, and brain exercising. You will have so much fun you will quit all the time! You will enjoy yourself so much while playing this game that you will NEVER recomend it to your friends because you want all of the brain pain to yourself! Enjoy the game! Use the google to figure out what sudoku is so that you can get the best explanation of the game.

## 21 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-21 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-24
| Team Name: | Apesh
| Team Members: | Aiden and Deepesh
| Project: | Sudoku
Division of Labor
| Module Name | Author
| Tasks Due | 2023-04-21 | Prriority
| Team Member | Tasks planned
| All | Decide on Project | 1
| All | Identify major parts of the project | 2
| All | Set up GitHub account and invite all participants | 3
| Plans for | 2023-04-24
| Team Member | Tasks planned
| All | Break up project into modules (use UML diagrams) | ?
| TBA | To Be Determined | ?
| TBA | To Be Determined | ?

## 24 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-24 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-25
| Team Name: | Apesh
| Team Members: | Aiden and Deepesh
| Project: | Sudoku
Division of Labor
| Module Name | Author
| Tasks Due | 2023-04-24 | Prriority
| Team Member | Tasks planned
| All | Break up project into modules (use UML diagrams) | ?
| TBA | To Be Determined | ?
| TBA | To Be Determined | ?
| Plans for | 2023-04-25
| Team Member | Tasks planned
| Aiden | Make Print Function for Sudoku | 1
| Deepesh | Write win() method in Sudoku.java | 2
| TBA | To Be Determined | ?

## 25 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-25 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-26
| Team Name: | Apesh
| Team Members: | Aiden and Deepesh
| Project: | Sudoku
Division of Labor
| Module Name | Author
| Tasks Due | 2023-04-25 | Prriority
| Team Member | Tasks planned
| Aiden | Make Print Function for Sudoku | 1 | Need to add values that are on the board
| Deepesh | Write win() method in Sudoku.java | 2 | DONE
| TBA | To Be Determined | ?
| Plans for | 2023-04-26
| Team Member | Tasks planned
| Aiden | Finish Print Function for Sudoku | 1
| Deepesh | Write reset() method in Sudoku.java | 2

## 26 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-26 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-27
| Team Name: | Apesh
| Team Members: | Aiden and Deepesh
| Project: | Sudoku
Division of Labor
| Module Name | Author
| Tasks Due | 2023-04-26 | Prriority
| Team Member | Tasks planned
| Aiden | Finish Print Function for Sudoku | 1 | DONE
| Deepesh | Write reset() method in Sudoku.java | 2 | DONE
| Plans for | 2023-04-27
| Team Member | Tasks planned
| Aiden & Deepesh | Integrate Print and reset | 1

## 27 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-27 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-28
| Team Name: | Apesh
| Team Members: | Aiden and Deepesh
| Project: | Sudoku
Division of Labor
| Module Name | Author
| Tasks Due | 2023-04-27 | Prriority
| Team Member | Tasks planned
| Aiden & Deepesh | Integrate Print and reset | 1 | DONE
| Plans for | 2023-04-28
| Team Member | Tasks planned for Project Presentration
| Aiden | Work on UI | 2
| Deepesh | Fix win() method | 1

## 28 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-28 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-01
| Team Name: | Apesh
| Team Members: | Aiden and Deepesh
| Project: | Sudoku
Division of Labor
| Module Name | Author
| Tasks Due | 2023-04-28 | Prriority
| Team Member | Tasks planned
| Aiden | Work on UI | 2 | Done
| Deepesh | Fix win() method | 1 | Done
| Plans for | 2023-05-01
| Team Member | Tasks planned for Project Presentration
| Deepesh & Aiden | Make Presentation for Sudoku | 1

## 1 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-05-01 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-02
| Team Name: | Apesh
| Team Members: | Aiden and Deepesh
| Project: | Sudoku
Division of Labor
| Module Name | Author
| Tasks Due | 2023-05-01 | Prriority
| Team Member | Tasks planned
| Deepesh & Aiden | Make Presentation for Sudoku | 1 | Need to add images and text to the slides
| Plans for | 2023-05-02
| Team Member | Tasks planned for Project Presentration
| Deepesh & Aiden | Make Presentation for Sudoku | 1

## 2 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-05-02 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-03
| Team Name: | Apesh
| Team Members: | Aiden and Deepesh
| Project: | Sudoku
Division of Labor
| Module Name | Author
| Tasks Due | 2023-05-02 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-05-03
| Team Member | Tasks planned for Project Presentration

## 3 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-05-03 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-04
| Team Name: | Apesh
| Team Members: | Aiden and Deepesh
| Project: | Sudoku
Division of Labor
| Module Name | Author
| Tasks Due | 2023-05-03 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-05-04
| Team Member | Tasks planned for Project Presentration

## 4 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-05-04 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-05
| Team Name: | Apesh
| Team Members: | Aiden and Deepesh
| Project: | Sudoku
Division of Labor
| Module Name | Author
| Tasks Due | 2023-05-04 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-05-05
| Team Member | Tasks planned for Project Presentration

## 5 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-05-05 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-08
| Team Name: | Apesh
| Team Members: | Aiden and Deepesh
| Project: | Sudoku
Division of Labor
| Module Name | Author
| Tasks Due | 2023-05-05 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-05-08
| Team Member | Tasks planned for Project Presentration

## Final
Scrum Reporting Form |  |  | Priority | Status | Final Thoughts on this Process
| Day | 2023-05-08 |  | Either DONE or what problem needs to be solved before the task can be completed. | This page is the last Scrum Form due and is to record your final thoughts on the process
| Due Day | Today
| Team Name: | Apesh
| Team Members: | Aiden and Deepesh
| Project: | Sudoku
Division of Labor
| Module Name | Author
| Tasks Due | 2023-05-08
| Team Member | Presentaion | Prriority
|  | Present slide show and program deminstration | 1
| Plans for | Today
| Team Member | Tasks planned
None - complete